## Summary
Employee | Hours Worked | Total Cost (EUR) | Avg Rate (EUR/h) | Entity
Clementine Roth | 294.55 | 13564.31 | 46.05 | 2017
Robert Gohla | 113.38 | 9157.28 | 80.77 | 2017
Daniela Chiran | 121.73 | 5944.92 | 48.84 | 2017
Mercedes Berlin | 82.09 | 4259.4 | 51.89 | 2017
Miljana Cosic | 64.63 | 3156.48 | 48.84 | 2017
TOTAL | 676.38 | 36082.39 | 53.3463

## Comparison vs Plan
Employee | Calculated Hours | Planned Hours | Difference (h) | Difference (%) | Total Cost (EUR) | Status
Robert Gohla | 113.38 | 155 | -41.62 | -26.9 | 9157.28 | ⚠ UNDER
Clementine Roth | 294.55 | 273.3 | 21.25 | 7.8 | 13564.31 | ⚠ OVER
Miljana Cosic | 64.63 | 75 | -10.37 | -13.8 | 3156.48 | ⚠ UNDER
Daniela Chiran | 121.73 | 115 | 6.73 | 5.9 | 5944.92 | ⚠ OVER
Mercedes Berlin | 82.09 | 80 | 2.09 | 2.6 | 4259.4 | ⚠ OVER

## Methodology
Step | Description | Formula
1. Data Source | DATEV payroll files (2016*.csv, 2017*.csv) - actual paid salaries | From DATEV exports
2. Monthly Cost | Sum of DATEV gesamtkosten for each person-month | SUM(gesamtkosten)
3. Hourly Rate | Monthly Cost / Total Hours Worked in that month | gesamtkosten / hours_worked
4. Project Hours | Time tracking entries allocated to ROBIN work packages (with prorata for multi-WP) | SUM(allocated_hours)
5. Project Cost | Hourly Rate × Project Hours (summed across all months) | Hourly_Rate × Project_Hours
6. Period | January 2025 to August 2025 (8 months) | 2025-01-01 to 2025-08-31
7. Total | Sum of all employees' project costs | 36,082.39 EUR